## Product Backlog
Epic ID | User Story ID | Feature Title | User Story | Priority | Acceptance Criteria | Status
EP-001 | US-001 | Search and Navigation | As a user, I want to search for products so that I can find specific items easily. | High | - User can type a query in the search bar. | New
- Search results are relevant and displayed within 2 seconds.
- Pagination works correctly.
EP-002 | US-002 | Shopping Cart and Checkout | As a user, I want to add items to my cart, so I can purchase them later. | High | - User can add multiple items to the cart. | New
- Cart retains items after refreshing the page.
- Cart shows correct price and quantity.
EP-002 | US-003 | Shopping Cart and Checkout | As a user, I want to apply discount coupons during checkout so that I can get a discount on my order. | Medium | - Coupon code can be entered at checkout. | New
- System validates correct and incorrect coupon codes.
- Correct discount is applied to the total price.
EP-001 | US-004 | Search and Navigation | As a user, I want to filter products by price range and brand to narrow down my search results. | Medium | - Price and brand filters work as expected. | New
- Filtering updates the product list without page reload.
- Filtered results match the criteria.
EP-003 | US-005 | Order Management | As a user, I want to track my order status after placing an order, so I know the current status. | High | - User can view order status on the "My Orders" page. | New
- Status updates dynamically (e.g., "Processing", "Shipped", "Delivered").
EP-004 | US-006 | User Account Management | As a user, I want to create an account, so I can save my shipping information for future purchases. | Medium | - User can register with email and password. | New
- Confirmation email is sent.
- User can log in with the correct credentials.
EP-005 | US-007 | Product Reviews | As a user, I want to view product reviews to help me make purchase decisions. | Low | - Reviews are visible on the product details page. | New
- Reviews are sorted by relevance or most recent.
- User can submit a review.
EP-006 | US-008 | Recommendations and Personalization | As a user, I want to see product recommendations based on my browsing history. | Low | - System shows personalized recommendations on the homepage. | New
- Recommendations update based on new user activity.
EP-002 | US-009 | Shopping Cart and Checkout | As a user, I want to complete my purchase through various payment options. | High | - User can select from multiple payment methods (credit card, UPI, net banking). | New
- Payment is processed successfully.
- Correct payment receipt is generated.

## Sprint Backlog
Epic ID | User Story ID | User Story | Task ID | Task Description | Assignee | Priority | Story Points | Status | Sprint
EP-001 | US-001 | As a user, I want to search for products so that I can find specific items easily. | T-001 | Develop and integrate the functionality. | Dev 1 | High | 5 | In Progress | 1
|  |  | T-002 | Write test cases for product search functionality. | Tester 1
|  |  | T-003 | Perform functional testing on search results. | Tester 3
EP-002 | US-002 | As a user, I want to add items to my cart, so I can purchase them later. |  |  | Dev 2 | High | 3 | To Do | 1
Tester 5
Tester 6
EP-002 | US-003 | As a user, I want to apply discount coupons during checkout so that I can get a discount on my order. |  |  | Dev 3 | Medium | 8 | To Do | 2
Tester 2
Tester 3
EP-001 | US-004 | As a user, I want to filter products by price range and brand to narrow down my search results. |  |  | Dev 1 | Medium | 5 | To Do | 2
Tester 5
Tester 6
EP-003 | US-005 | As a user, I want to track my order status after placing an order, so I know the current status. |  |  | Dev 2 | High | 3 | In Progress | 1
Tester 2
EP-004 | US-006 | As a user, I want to create an account, so I can save my shipping information for future purchases. |  |  | Dev 3 | Medium | 5 | Done | 2
Tester 4
Tester 5
EP-005 | US-007 | As a user, I want to view product reviews to help me make purchase decisions. |  |  | Dev 4 | Low | 2 | To Do | 3
Tester 1
Tester 2
EP-006 | US-008 | As a user, I want to see product recommendations based on my browsing history. |  |  | Dev 5 | Low | 8 | Backlog | 3
Tester 4
EP-002 | US-009 | As a user, I want to complete my purchase through various payment options. |  |  | Dev 1 | High | 8 | Backlog | 1
Tester 6
Tester 2

## Task
Task ID | SPOC | Team Name
T-001 | Dev 1 | Front end Team
T-002 | Tester 1 | UI/UX Team